## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | David | Tarik | Jonathan | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 10 |  | 10
Start: 9/16 |  | Design architecture | Project Manager | David | 10 |  | 10 |  | 10 |  |  | 10
End: 12/2 | Requirements |  |  |  |  | 7 |  | 6
11 Weeks |  | Gather | Requirements Engineer | Jonathan | 3 |  | 1 |  |  |  | 1 | 1
|  | Analyze | Requirements Engineer | Jonathan | 2 |  | 2 |  |  |  | 2 | 2
|  | Specify | Requirements Engineer | Jonathan | 2 |  | 3 |  |  |  | 3 | 3
| Documentation |  |  |  |  | 24.5 |  | 18
| 2019-09-20 | Project Charter | Project Manager | David, Jonathan | 2 |  | 4 |  | 1 | 1 | 2 | 4
| 2019-09-23 | Requirements Document | Project Manager, Requirements Engineer | David, Jonathan | 4 |  | 4 |  | 1 | 1 | 2 | 4
| 2019-09-27 | Project Plan | Project Manager, Developers | All | 3 |  | 5 |  | 1 | 4 |  | 5
| 2019-10-07 | Technical Prototype | All | All | 5 |  | 4 |  | 2 | 2 |  | 4
| 2019-10-28 | Project Status | Project Manager | David | 0.5 |  | 1 |  | 1 |  |  | 1
| 2019-11-01 | Architecture Document | Architect | David | 3
| 2019-11-22 | Test Report | Tester | Tarik | 4
| 2019-12-01 | User Guide & System Admin Doc | Developers, Requirements Engineer | All | 3
Iteration 1: | Design |  |  |  |  | 5 |  | 6
Start: 9/16 |  | Design database | Database Administrator | Jonathan | 2 |  | 3 |  |  | 2 | 1 | 3
End: 9/30 |  | Website prototype | Project Manager | David | 3 |  | 3 |  | 3 |  |  | 3
2 Weeks | Development |  |  |  |  | 15 |  | 17
|  | Determine technology needs | Project Manager | David | 1 |  | 2 |  | 2 |  |  | 2
|  | Research and learn new language and environment | All | All | 10 |  | 12 |  | 4 | 4 | 4 | 12
|  | Setup database | Database Administrator | All | 4 |  | 3 |  |  | 1 | 2 | 3
| Analysis |  |  |  |  | 3 |  | 5
|  | Evaluate needs for next iteration | Project Manager | David | 3 |  | 5 |  | 5 |  |  | 5
Iteration 2: | Design |  |  |  |  | 1 |  | 2
Start: 9/30 |  | Decide Framework (ASP.NET Core MVC) | Project Manager, Developers | David, Jonathan | 1 |  | 2 |  | 1 |  | 1 | 2
End: 10/14 | Development |  |  |  |  | 27 |  | 25
2 Weeks |  | Create Database with Server (MySQL on UMKC Server) | Database Administrator | Jonathan, Tarik | 4 |  | 3 |  |  | 1 | 2 | 3
|  | Create login | Developers | All | 3 |  | 2 |  | 1 |  | 1 | 2
|  | Create homepage | Developers | All | 5 |  | 5 |  | 3 |  | 2 | 5
|  | Create transactions page | Developers | All | 2 |  | 2 |  | 2 |  |  | 2
|  | Create rules page | Developers | All | 2 |  | 4 |  | 1 |  | 3 | 4
|  | Create alerts & reports pages | Developers | All | 3 |  | 3 |  | 2 |  | 1 | 3
|  | Create project and layout view | Developers | All | 2 |  | 2 |  | 1 |  | 1 | 2
|  | Connect website to database | Developers | All | 6 |  | 4 |  |  | 3 | 1 | 4
| Analysis |  |  |  |  | 7 |  | 6
|  | Evaluate needs for next iteration | Project Manager | David | 3 |  | 3 |  | 3 |  |  | 3
|  | Bug fixes | Tester | All | 2 |  | 1 |  |  | 1 |  | 1
|  | System check | Testers | David, Jonathan | 2 |  | 2 |  |  | 1 | 1 | 2
Iteration 3: | Design |  |  |  |  | 6 |  | 3
Start: 10/14 |  | Add multi account support | Developers | Jonathan, David | 3 |  | 2 |  |  |  | 2 | 2
End: 10/28 |  | Standardize database | Database Adminstrator | Tarik, Jonathan | 3 |  | 1 |  |  |  | 1 | 1
2 Weeks | Development |  |  |  |  | 13 |  | 3
|  | Add triggers to database | Developer | Jonathan | 2 |  | 1 |  |  |  | 1 | 1
|  | Ability to remove alerts | Developers | David, Jonathan | 1 |  | 0
|  | Generate reports based on certain time period | Developer | David | 2 |  | 2 |  | 2 |  |  | 2
|  | Handle session timeouts | Developer | Jonathan | 3 |  | 0
|  | Block SQL injections | Developers | All | 5 |  | 0
| Analysis |  |  |  |  | 7 |  | 10
|  | Evaluate needs for next iteration | Project Manager | David | 3 |  | 5 |  | 5 |  |  | 5
|  | Bug fixes | Tester | All | 2 |  | 2 |  |  | 1 | 1 | 2
|  | System check | Testers | David, Jonathan | 2 |  | 3 |  | 1 | 1 | 1 | 3
Iteration 4: | Design |  |  |  |  | 4 |  | 0
Start: 10/28 |  | Add multi-account support | Developer | Jonathan | 2
End: 11/11 |  | Database API | Database Adminstrator | Tarik, Jonathan | 2
2 Weeks | Development |  |  |  |  | 16 |  | 0
|  | Ability to remove alerts | Developer | David | 3
|  | Handle session timeouts | Developer | Jonathan | 2
|  | Block SQL injections | Developers | All | 5
|  | Add database data to reports export | Developers | David | 1
|  | Unit testing | Developers | All | 5
| Analysis |  |  |  |  | 7 |  | 0
|  | Evaluate needs for next iteration | Project Manager | David | 2
|  | Bug fixes | Tester | All | 3
|  | System check | Testers, Developers | David, Jonathan | 2
Iteration 5: | Design |  |  |  |  | 0 |  | 0
Start: 11/11
End: 12/2 | Development |  |  |  |  | 0 |  | 0
3 Weeks
| Analysis |  |  |  |  | 0 |  | 0
Total |  |  |  |  | 152.5 | 152.5 | 111 | 111 | 52 | 23 | 36 | 111